## AR List
Header | ARs | Owner | ECD | Comments
Building/Testing the Cars
Basic Car Kit | Build the Car | Allison/David | WW06 | Allison/David - order parts Core Team - help with the coding Team - Build the cars
Intermediat Car Kit | Build the Car
Advanced Car Kit | Build the Car
Coding the Cars/Documenting the Scripts
Basic Car Kit | Code the Basic Car | Core Team
Int. Car Kit | Code the Intermediate Car
Adv. Car Kit | Code the Advanced Car
Negotiating with Device Depot
Device Depot | Meet with Peter Lopez, Device Depot | Dan, David, Allison | WW06.5
Device Depot
Device Depot
Device Depot
Funding the Project
Funding/Sponsor | Create the Final BOM list | Core Team | WW07 | Present documentation to Joan, ask what are the next steps for funding. Who do we go to?
Funding/Sponsor
Funding/Sponsor
Create 20 Car Kit components
IMR | Ready in time for the 1st event | David
IMR
Header | ARs | Owner | ECD | Comments
Documentation for Event
Training Materials | Create the Job Aid | ISD/Core Team
Training Materials | Create the presentation | ISD/Core Team
Training Materials | Create the Scripts | ISD/Core Team
Training Materials | Choose 3 Makers from the Maker group and have them put together the Cars with the Training Materials available | Core Team |  | Bring in ISD person and Phil Banks to take video.
Event Planning
Event | Prep work | Todd
Event | Launch | Todd
Event | Food | Todd |  | Allison can help if needed
Event | Build the race and obstacle courses | Todd/Russ
SparkFun | Contact SparkFun - see if they would like to be involved in the event | David/Noel
Event | Talk to Tom in Automation to provide a Mini Event Network | David
Planet Blue | Market event, add zip file, etc. to Inside Blue Makers site. | Allison
Feedback
Participation | Use of maker space, # of families signed up, # of families with prototype, attendance | Allison/ ISD person
Participation | GPTW Metrics, BYCTW Metrics
Family Maker Morale | Survey at the beginning and end of event
Networking within/without the departments engaged | Direct Observation, Rosters, Participation lists
Header | ARs | Owner | ECD | Comments
Upskilling in hardware/software | End of Course Surveys | Allison/ ISD person
Member count | count/Likes on Maker Family Inside Blue site (internal and external)
Mentions in the press | Arduino, Intel Maker Families, etc. (monitor news articles)
Ambassadors for Intel | Intel presence in NM State (monitor local events which Maker Families participate in)
Additional ARs
Recognition Badges | Investigate using SparkFun recognition badge kits for kids to take home with them | Janet / Todd / David
Thumb Drive download | Zip library files and put on the thumb drives for event | Core Team

## BOM
Beginner Base Kit
DEV-09815 | Sparkfun Ardumoto - Motor Driver Shield | 19.96
PRT-10007 | Arduino Stackable Header Kit | 1.2
ROB-13259 | Wheel - 65mm (Rubber Tire, Pair) | 2.36
ROB-13302 | Hobby Gearmotor - 140 RPM (Pair) | 3.16
ROB-12629 | Wheel Encoder Kit | 10.36
PRT-00115 | Female Headers | 1.2
PRT-0016 | Break Away Header - Straight | 1.2
PRT-13156 | Header - 2x8 (Male, 0.1") | 0.76
PRT-11269 | Female Header Pack | 1.2
PRT-08233 | Polarized Connectors - Header (2-Pin) | 0.36
PRT-00091 | 9V Snap Connector | 1
ROB-13301 | Shadow Chassis | 10.36
DEV-13787 | Arduino 101 | 30
PRT-12794 | Jumper Wires - Connected 6\" (M/F, 20 pack) | 1.56
PRT-12795 | Jumper Wires - Connected 6\" (M/M, 20 pack) | 1.56
| Sub-Total | 86.24
Intermediate Addons
COM-12877 | LED RGB Addressable, PTH, 8mm (5pack) | 2.36
ROB-12567 | SparkFun RedBot Buzzer | 4.76
| Sub-Total | 7.12
Advanced Addons
CAB-13685 | JST to Breadboard Jumper (3-pin) | 1.2
SEN-12728 | Infrared Proximity Sensor Short Range - Sharp GP2Y0A41SK0F | 11.16
ROB-09065 | Servo - Generic (Sub-Micro Size) | 7.16
| Sub-Total | 19.52
| Curie Classic Device Depot Kit (Beginner, Intermediate and Advanced) | 112.88

## Pins
| MotorA | MotorB | EncA | EncB | Buzzer | Servo | ProximitySensor | RGB LED
PWR 5 |  |  | X | X |  |  | X | X
GND |  |  | X | X | X |  | X | X
DIO | 12 3PWM | 13 11->9PWM |  |  | 5PWM | 6PWM |  | 7
AIO |  |  | A0 | A1 |  |  | A2
DIO | 0, 1, 2, 4, 8, 10
AIO | A3, A4, A5