## Sheet1
| Sun | Mon | Tue | Wed | Thurs | Fri | Sat
WW08 | 2016-02-14 | 2016-02-15 | 2016-03-16 | 2016-02-17 | 2016-02-18 | 19-Feb Let's Build | 20-Feb Order Parts
WW09 | 2016-02-21 | Device Depot Work - Surveys, etc. |  |  |  | 26-Feb Built first Prototypes | 2016-02-27
WW10 | 2016-02-28 | 2/29/2016 order Adafruit supplies |  |  |  | Let's Build Continued building Prototypes | 2016-03-05
WW11 | 2016-03-06 | Materials, Revision, GitHub and Coding Work |  |  |  | 11-Mar Prototypes complete New BOM Ordered Arduino Boards | 2016-03-12
WW12 | 2016-03-13 | Order New BOM Request Device Depot pays for tool boxes Frameworks 12, Documentation of Training, Pictures and Video |  |  |  | 18-Mar Kits Complete | 2016-03-19
WW13 | 2016-03-20 | IMR Solders, builds additional pieces Finish coding scripts Allison OOP on the 22nd and 23rd |  |  |  | 25-Mar Testing Complete Team creates kits in the tool boxes | 2016-03-26
WW14 | 2016-03-27 | Marketing and Branding, signage Build and Test documentation with Maker Family Create presentations for lead instructor Define roles to play |  |  |  | April-1 Documentation Complete | 2016-04-02
WW15 | 2016-04-03 | Build Racetrack |  | 6-April Maker Kickoff Announce Event Volunteer sign-up |  | 8-April Racetrack Complete | 2016-04-09
WW16 | 2016-04-10 | Volunteer Maker Training Rollout |  |  |  | 15-Apr Volunteer Training Complete | 2016-04-16
WW17 | 2016-04-17 | Secure Food, facility, electrical strips, tools, microphones, Wi-Fi setup |  |  |  |  | 23-Apr Beginner Event Intermediate/Expert
WW18 | 2016-04-24 | Make Adjustments