## AR List
Header | ARs | Owner | ECD | Comments
Building/Testing the Cars
Basic Car Kit | Build the Car | Allison/David | WW06 | Allison/David - order parts Core Team - help with the coding Team - Build the cars
Intermediat Car Kit | Build the Car
Advanced Car Kit | Build the Car
Coding the Cars/Documenting the Scripts
Basic Car Kit | Code the Basic Car | Core Team
Int. Car Kit | Code the Intermediate Car
Adv. Car Kit | Code the Advanced Car
Negotiating with Device Depot
Device Depot | Meet with Peter Lopez, Device Depot | Dan, David, Allison | WW06.5
Device Depot
Device Depot
Device Depot
Funding the Project
Funding/Sponsor | Create the Final BOM list | Core Team | WW07 | Present documentation to Joan, ask what are the next steps for funding. Who do we go to?
Funding/Sponsor
Funding/Sponsor
Create 20 Car Kit components
IMR | Ready in time for the 1st event | David
IMR
Header | ARs | Owner | ECD | Comments
Documentation for Event
Training Materials | Create the Job Aid | ISD/Core Team
Training Materials | Create the presentation | ISD/Core Team
Training Materials | Create the Scripts | ISD/Core Team
Training Materials | Choose 3 Makers from the Maker group and have them put together the Cars with the Training Materials available | Core Team |  | Bring in ISD person and Phil Banks to take video.
Event Planning
Event | Prep work | Todd
Event | Launch | Todd
Event | Food | Todd |  | Allison can help if needed
Event | Build the race and obstacle courses | Todd/Russ
SparkFun | Contact SparkFun - see if they would like to be involved in the event | David/Noel
Event | Talk to Tom in Automation to provide a Mini Event Network | David
Planet Blue | Market event, add zip file, etc. to Inside Blue Makers site. | Allison
Feedback
Participation | Use of maker space, # of families signed up, # of families with prototype, attendance | Allison/ ISD person
Participation | GPTW Metrics, BYCTW Metrics
Family Maker Morale | Survey at the beginning and end of event
Networking within/without the departments engaged | Direct Observation, Rosters, Participation lists
Header | ARs | Owner | ECD | Comments
Upskilling in hardware/software | End of Course Surveys | Allison/ ISD person
Member count | count/Likes on Maker Family Inside Blue site (internal and external)
Mentions in the press | Arduino, Intel Maker Families, etc. (monitor news articles)
Ambassadors for Intel | Intel presence in NM State (monitor local events which Maker Families participate in)
Additional ARs
Recognition Badges | Investigate using SparkFun recognition badge kits for kids to take home with them | Janet / Todd / David
Thumb Drive download | Zip library files and put on the thumb drives for event | Core Team

## BOM
Beginner Base Kit |  | Single | Bulk (20) | Spares |  | Need to have 20 kits | Digikey | Mouser | Sparkfun | BP | Amazon | IMR 3D Prints for 20 kits
DEV-09815 | Sparkfun Ardumoto - Motor Driver Shield | 19.96 | 399.2 |  |  | Max of 3000 | 31.4 | 301.86 | 1156.68 | 564.61 | 160.2 | 172 | Invoice totals
PRT-10007 | Arduino Stackable Header Kit Qty: 2 | 2.4 | 48 |  |  |  | 3wire cable not all used with just 20 | 64.8 |  |  |  | 2321.95 | Sub-Totals
ROB-13259 | Wheel - 65mm (Rubber Tire, Pair) | 2.36 | 47.2 |  |  |  | Racetrack Budget |  |  |  |  | 613.25
ROB-13302 | Hobby Gearmotor - 140 RPM (Pair) | 3.16 | 63.2 | 3 | 72.68
ROB-12629 | Wheel Encoder Kit @10.36 (only 19 ordered OR does not want this) | 10.36 | 196.84 | 3 | 227.92 | Back Ordered
PRT-08233 | Polarized Connectors - Header (2-Pin) | 0.36 | 7.2
PRT-00091 | 9V Snap Connector | 1 | 20
BH26AASF-AS-ND | Battery Holder 6AA | 1.74 | 31.4
ROB-13301 | Shadow Chassis | 10.36 | 207.2 | 1 | 217.56
DEV-13787 | Arduino 101 from BP Store | 26 | 520
Amazon | Omall (TM) 40PIN 20cm 1P-1P Male to Male Breadboard Cable Jump Wire Jumper For Arduino(Pack of 2) @7.99 purchase 4 Qty: need 15 /kit include 16/kit | 1.578 | 31.56
Amazon | Omall (TM) 40pin 300mm 1P-1P Male to Female Breadboard Cable Jump Wire Jumper For Arduino(Pack of 2) @7.99 for proximity sensor Qty: need 3/kit include 4/kit | 0.3995 | 7.99
Amaxon | Cable Matters (3 Pack) Hi-Speed USB 2.0 Type A to B Printer Scanner Cable - 3 Feet @ 8.99 puchase 7 Qty: need 1/kit | 3.1465 | 62.93
| Sub-Total | 82.824 | 1642.72
Intermediate Addons |  | Single | Bulk (20)
COM-12877 | LED RGB Addressable, PTH, 8mm (5pack) | 2.36 | 47.2 | 3 | 54.28
810-PS1240P02BT | Piezo Buzzer Audio Indicators & Alerts Round 12.2mmx6.5mm 4kHz Vin=3V | 0.72 | 12.44 | 3 | 14.31
3-640440-4 | Headers & Wire Housings 4P 22AWG TIN CLSD W/O TAB W/RED STRIPE Qty: 2 | 0.54 | 7.32 | 6 | 8.42
3-640620-4 | Headers & Wire Housings FEED THRU W/O TAB 4P red tin 22 AWG Qty: 3 | 1.02 | 19.62 | 9 | 22.56
640550-4 | Headers & Wire Housings DUST COVER 4P Closed End QTY: 2 | 0.32 | 5.2 | 6 | 5.98
640642-4 | Headers & Wire Housings DUST COVER 4P Feed-Thru QTY: 3 | 0.54 | 8.22 | 9 | 9.45
82-22-6103 | ** Flat Cables Rib Cbl .100 100ft Rl Tin 3Ckt 22awg @ $108 Need 2ft / Chassis ** Order this item per 50 Kits | 2.16 | 43.2
| Sub-Total | 7.66 | 143.2
Advanced Addons |  | Single | Bulk (20)
CAB-13685 | JST to Breadboard Jumper (3-pin) | 1.2 | 24 | 3 | 27.6
852-GP2Y0A41SK0F | Proximity Sensors Dist Meas Sensor Analog, 4-30 cm | 7.54 | 124.4
Amazon | Tizzy-BAC ® 10pcs *Rc Mini Micro 9g 1.6KG Servo SG90 for RC 250 450 Helicopter Airplane Car Boat @ 20.99 purchase 2 Qty: need 1 / kit | 2.099 | 41.98 | 5 | 53.46
| Sub-Total | 10.839 | 190.38
IMR Provided 3D Printed Parts |  | Single | Bulk (20)
IMR-RacerLED | 8mm RGB LED Holder QTY: 4 | 2.6 | 52 | 1.82
IMR-RacerBatt | 9V Battery Holder | 1.55 | 31 | 4.55
IMR-RacerPSens | Proximity Sensor Holder | 3.3 | 66 | 1.885
IMR-RacerServo | Servo Holder | 1.15 | 23 | 2.08
| Sub-Total | 8.6 | 172 | 10.335
|  | Single | Bulk of 20 per unit cost
| Intel Maker Nation NM Racer Kit (Beginner, Intermediate and Advanced) | 109.923 | 107.415
| NM racetrack Budget | 613.25

## Pins
| MotorA | MotorB | EncA | EncB | Buzzer | Servo | ProximitySensor | RGB LED
PWR 5 |  |  | X | X |  | X | X | X
GND |  |  | X | X | X | X | X | X
DIO | 12 3PWM | 13 11->9PWM | 2 | 8 | 5PWM | 6PWM |  | 7
AIO | [6 empty] | A0
DIO | 0, 1, 4, 10
AIO | A1,A2,A3, A4, A5
Wires Required
| direct connect to shield | direct connect to shield White | Red Black White | Red Black White | Black White | Red Black White | JST to Breadboard Cable Red Black Yellow | Red Black White
From Power Pin of Shield to Male Header |  |  |  | Red
From Ground pin of shield to Female Header |  |  |  | Black
PWR 5V | M-M | Red | 5 -> 3 |  | Shield side need (6 w/encoders) 4 pin Header for Power
| M-F | Red | 1 |  | Pwr to Proximity sensor
| M-M | Red | 1 |  | 5V to pwr header
GND | M-M | Black | 6 -> 4 |  | Shield side need (7 w/encoders) 5 pin Header for Ground
| M-F | Black | 1 |  | Gnd to Proximity sensor
| M-M | Black | 1 |  | Gnd to gnd header
Signal | M-M | White | 5 |  | To IO pins Female header on shield
| M-M | White | 1 |  | 9 to 11 jumper
| M-F | Yellow | 1 |  | A0 to Proximity Sensor
| M-M | 15
| M-F | 3