## AR List
Header | ARs | Owner | ECD | Comments
Building/Testing the Cars
Basic Car Kit | Build the Car | Allison/David | WW06 | Allison/David - order parts Core Team - help with the coding Team - Build the cars
Intermediat Car Kit | Build the Car
Advanced Car Kit | Build the Car
Coding the Cars/Documenting the Scripts
Basic Car Kit | Code the Basic Car | Core Team
Int. Car Kit | Code the Intermediate Car
Adv. Car Kit | Code the Advanced Car
Negotiating with Device Depot
Device Depot | Meet with Peter Lopez, Device Depot | Dan, David, Allison | WW06.5
Device Depot
Device Depot
Device Depot
Funding the Project
Funding/Sponsor | Create the Final BOM list | Core Team | WW07 | Present documentation to Joan, ask what are the next steps for funding. Who do we go to?
Funding/Sponsor
Funding/Sponsor
Create 20 Car Kit components
IMR | Ready in time for the 1st event | David
IMR
Header | ARs | Owner | ECD | Comments
Documentation for Event
Training Materials | Create the Job Aid | ISD/Core Team
Training Materials | Create the presentation | ISD/Core Team
Training Materials | Create the Scripts | ISD/Core Team
Training Materials | Choose 3 Makers from the Maker group and have them put together the Cars with the Training Materials available | Core Team |  | Bring in ISD person and Phil Banks to take video.
Event Planning
Event | Prep work | Todd
Event | Launch | Todd
Event | Food | Todd |  | Allison can help if needed
Event | Build the race and obstacle courses | Todd/Russ
SparkFun | Contact SparkFun - see if they would like to be involved in the event | David/Noel
Event | Talk to Tom in Automation to provide a Mini Event Network | David
Planet Blue | Market event, add zip file, etc. to Inside Blue Makers site. | Allison
Feedback
Participation | Use of maker space, # of families signed up, # of families with prototype, attendance | Allison/ ISD person
Participation | GPTW Metrics, BYCTW Metrics
Family Maker Morale | Survey at the beginning and end of event
Networking within/without the departments engaged | Direct Observation, Rosters, Participation lists
Header | ARs | Owner | ECD | Comments
Upskilling in hardware/software | End of Course Surveys | Allison/ ISD person
Member count | count/Likes on Maker Family Inside Blue site (internal and external)
Mentions in the press | Arduino, Intel Maker Families, etc. (monitor news articles)
Ambassadors for Intel | Intel presence in NM State (monitor local events which Maker Families participate in)
Additional ARs
Recognition Badges | Investigate using SparkFun recognition badge kits for kids to take home with them | Janet / Todd / David
Thumb Drive download | Zip library files and put on the thumb drives for event | Core Team

## BOM
Beginner Base Kit |  |  |  |  | Need to have 20 kits
DEV-09815 | Sparkfun Ardumoto - Motor Driver Shield | 19.96 |  |  | Max of 3000
PRT-10007 | Arduino Stackable Header Kit Qty: 2 | 2.4 |  |  | need to include racetrack material
ROB-13259 | Wheel - 65mm (Rubber Tire, Pair) | 2.36 | bulk
ROB-13302 | Hobby Gearmotor - 140 RPM (Pair) | 3.16 | bulk |  | Research bulk quantity of parts
ROB-12629 | Wheel Encoder Kit | 10.36 | drop | 10.36
PRT-08233 | Polarized Connectors - Header (2-Pin) | 0.36
PRT-00091 | 9V Snap Connector | 1
ROB-13301 | Shadow Chassis | 10.36
DEV-13787 | Arduino 101 | 30 | bpstore | 4
PRT-08431 | Jumper Wires Premium 6" M/M Pack of 10 Qty: 3 | 9.48 | bulk
| Sub-Total | 89.44
Intermediate Addons
COM-12877 | LED RGB Addressable, PTH, 8mm (5pack) | 2.36
ROB-12567 | SparkFun RedBot Buzzer | 4.76 | research piezo in bulk | 3.2
3-640440-4 | Headers & Wire Housings 4P 22AWG TIN CLSD W/O TAB W/RED STRIPE Qty: 2 | 0.54
3-640620-4 | Headers & Wire Housings FEED THRU W/O TAB 4P red tin 22 AWG Qty: 3 | 1.02
640550-4 | Headers & Wire Housings DUST COVER 4P Closed End QTY: 2 | 0.32
640642-4 | Headers & Wire Housings DUST COVER 4P Feed-Thru QTY: 3 | 0.54
82-22-6103 | ** Flat Cables Rib Cbl .100 100ft Rl Tin 3Ckt 22awg @ $108 Need 2ft / Chassis ** Order this item per 50 Kits | 2.16
| Sub-Total | 11.7
Advanced Addons
CAB-13685 | JST to Breadboard Jumper (3-pin) | 1.2
SEN-12728 | Infrared Proximity Sensor Short Range - Sharp GP2Y0A41SK0F | 11.16 | look for cheaper sensor
ROB-09065 | Servo - Generic (Sub-Micro Size) | 7.16
| Sub-Total | 19.52
IMR Provided 3D Printed Parts
IMR-RacerLED | 8mm RGB LED Holder QTY: 4 | 2.6
IMR-RacerBatt | 9V Battery Holder | 1.55
IMR-RacerPSens | Proximity Sensor Holder | 3.3
IMR-RacerServo | Servo Holder | 1.15
| Sub-Total | 8.6
| Intel Maker Nation Device Depot Racer Kit (Beginner, Intermediate and Advanced) | 129.26 |  | 17.56
111.7
| 19 kits | 2122.3
| racetrack and spares | 877.7
USB B cables

## Pins
| MotorA | MotorB | EncA | EncB | Buzzer | Servo | ProximitySensor | RGB LED
PWR 5 |  |  | X | X |  | X | X | X
GND |  |  | X | X | X | X | X | X
DIO | 12 3PWM | 13 11->9PWM | 2 | 8 | 5PWM | 6PWM |  | 7
AIO | [6 empty] | A0
DIO | 0, 1, 4, 10
AIO | A1,A2,A3, A4, A5
Wires Required
| direct connect to shield | direct connect to shield White | Red Black White | Red Black White | Black White | Red Black White | JST to Breadboard Cable Red Black Yellow | Red Black White
From Power Pin of Shield to Male Header |  |  |  | Red
From Ground pin of shield to Female Header |  |  |  | Black
PWR 5V | M-M | Red | 5 |  | Shield side need 6 pin Header for Power
GND | M-M | Black | 6 |  | Shield side need 7 pin Header for Ground
Signal | M-M | White | 6 |  | To IO pins Female header on shield
| M-M | white | 9 to 11
| M-F | yellow | A0 to Proximity Sensor
| M-F | red | Pwr to Proximity sensor
| M-F | black | Gnd to Proximity sensor
| M-M | red | 5V to pwr header
| M-M | black | Gnd to gnd header
need an extra pin on pwr header